## task1
ID | Active | Task_Mode | Task_Name | Duration | Start_Date | Finish_Date | Predecessors | Resource_Names
0 | Yes | Auto Scheduled |  | 62 days | 23 November 2022 10:00 | 24 February 2023 20:00
1 | Yes | Auto Scheduled | SCADA PROJECT DEVELOPMENT | 62 days | 23 November 2022 10:00 | 24 February 2023 20:00
2 | Yes | Auto Scheduled | Automation Concept Development | 20 days | 23 November 2022 10:00 | 20 December 2022 20:00
3 | Yes | Auto Scheduled | Preliminary analysis and data taking | 20 days | 23 November 2022 10:00 | 20 December 2022 20:00 |  | Project Controller [50%],Project Manager [50%]
4 | Yes | Auto Scheduled | Hardware development & Implemention | 20 days | 21 December 2022 10:00 | 25 January 2023 20:00 | 2,3
5 | Yes | Auto Scheduled | Hardware development | 10 days | 21 December 2022 10:00 | 10 January 2023 20:00 | 2,3 | Cable[6 Rolls],Operators
6 | Yes | Auto Scheduled | Hardware installation | 10 days | 11 January 2023 10:00 | 25 January 2023 20:00 | 5 | Technicians in Automation
7 | Yes | Auto Scheduled | Software Development & Implementation | 20 days | 04 January 2023 10:00 | 01 February 2023 20:00 | 4SS+5d
8 | Yes | Auto Scheduled | software Development | 10 days | 04 January 2023 10:00 | 18 January 2023 20:00 | 4SS+5d | Operators[200%],System Analyst
9 | Yes | Auto Scheduled | software Implementation | 10 days | 19 January 2023 10:00 | 01 February 2023 20:00 | 8 | System Analyst,Technicians in Automation
10 | Yes | Auto Scheduled | Start Up | 10 days | 02 February 2023 10:00 | 15 February 2023 20:00 | 7,8
11 | Yes | Auto Scheduled | System Documentation | 7 days | 16 February 2023 10:00 | 24 February 2023 20:00 | 10